PROJECT WORK PROPOSAL

LEARNER’S NAME: BAGUMA SSENTAMU RICHARD

CENTER NUMBER:					 YEAR: 2024

LEARNER’S ID:

  - Identification of a project

I intend to make a good dustbin for my class which can reduce on littering in our environment. To come up with a good dustbin, I intend to check on google to see various models, get some knowledge from my classmates, teachers, cleaners and carpenters

  - Project title

My project title will be MAKING A DUSTBIN TO REDUCE ON LITTERING IN THE ENVIRONMENT

  - Purpose of the project

The purpose of the project will be; To make a dustbin that can help reduce littering in our school environment

  - Project Objective

The objective of my project will be; To make a dustbin that can help reduce littering in our classroom

  - Justification of the project

I tend to do a project of a dustbin because there’s a lot of littering in our school environment my class inclusive. In my classroom, we don’t have any dustbin where learners can dump their waste and I hope by making one, I would have helped to preserve our environment from poor disposal of waste

  - Identification of resources for the project

I will use the following resources to come up with the above project

- I will use bottles to build up a unique dustbin

- I will use wood glue to attach bottles together

- I will need a polythene bag to catch rubbish from falling through the gaps left by bottles

  - Project activity/ plan

| DATE | HOURS | ACTIVITY | COSTS | IN-CHARGE |
| --- | --- | --- | --- | --- |
| 22nd July 2024 | 5:00-7:00 AM | Writing a proposal | Nil | Baguma Ssentamu |
| 22nd July 2024 | 4:40-5:20 PM | Handing proposal to the supervisor | Nil | Baguma Ssentamu |
| 23rd July 2024 | 5:00-7:00 AM | Making revisions of my proposal | Nil | Baguma Ssentamu |
| 23rd July 2024 | 4:40-5:20 PM | Handing in final proposal | Nil | Baguma Ssentamu |
| 24th July 2024 | 4:40-6:00 PM | Collecting bottles and glue for projects | 6500/= for glue | Baguma Ssentamu |
| 25th July 2024 | 4:40-6:00 PM | Collecting more bottles for the project | Nil | Baguma Ssentamu |
| 26th July 2024 | 4:40-6:00 PM | Assembling bottles to come up with a dustbin | Nil | Baguma Ssentamu |
| 27th July 2024 | 4:40-6:00 PM | Assembling more bottles to come up with a dustbin | Nil | Baguma Ssentamu |
| 28th July 2024 | 4:40-6:00 PM | Assembling more bottles to come up with a dustbin | Nil | Baguma Ssentamu |
| 29th July 2024 | 4:40-6:00 PM | Fixing in a polythene bag to complete my dustbin | Nil | Baguma Ssentamu |
| 30th July 2024 | 4:40-6:00 PM | Handing in my dustbin to the teacher for approval | Nil | Baguma Ssentamu |
| 31st July 2024 | 4:40-6:00 PM | Making corrections basing on teacher’s guidance | Nil | Baguma Ssentamu |
| 1st July 2024 | 4:40-6:00 PM | Dissemination of the product | Nil | Baguma Ssentamu |
| 2nd July 2024 | 4:40-6:00 PM | Writing a project report | Nil | Baguma Ssentamu |
| 3rd July 2024 | 4:40-6:00 PM | Handing in all necessary requirements for the project to the supervisor | Nil | Baguma Ssentamu |

  - In doing my project, I will integrate the following subjects

- English (My project proposal and report shall be written in English language)

- Geography (The dustbin shall be made using bottles for recycling of waste products and the dustbin shall promote environmental conservation

- Art and Design (To be used in designing my dustbin on paper)

- ICT (ICT shall be used in making research on various models of a dustbin

- Mathematics (Mathematics knowledge will be highly applicable in measurement of the dustbin materials needed at each stage)

  - Integration of knowledge and skills

I will incorporate the following cross cutting issues in coming up with the above product

- Environmental awareness by cleaning up my area of work

- I will put on gloves during work to be safe from damaging my body

- I will use a mixture of abilities including art, maths, drawing, ICT, etc.

- I will use only 7500/= on my whole project

1.10 Demonstration of generic skills

I will demonstrate the following generic skills during the process

- Cooperation with my supervisors and fellow students

- Effective communication with my supervisors and fellow students to get help

- Critical thinking to come up with a unique dustbin

- Mathematical computation to come up with an accurate dustbin

- ICT proficiency to come up with the best product